## Instruction
Document information
Title | Guidance | Information
Project | What Project is the Plan for? | Project Name
Title | What is the title of this document? | Information Management Plan - Organizational
Quality | Who performed the quality check on this document? | Checked PL / Reviewed PL / Approved PL
Document File Naming | What is this document's file naming? | InformationManagementPlan-Organisational.xlsx
Version | What is this document's current version? | A01.01 - 19/12/2023
Template Instructions
Colour and font | Guidance | Example
sentence in grey italics | This represents what is required as a response in plain language | Why and what is the information needed?
red italics | This represents guidance on completing the document | Add Hyperlink
red | This represents an example of suitable text | Fire Safety Certificate Report
Tables | Purpose | Response required
OIR (Organizational information requirements) | identify what information is required for the organisation to function | individuals in the organisation identify the information they need to perform their duties
AIR (Asset information requirements) | identify what information is required to operate the asset | the asset manager/operator identifies the information they need to operate the asset correctly
PIR (Project information requirements) | identify what information is required to deliver (design/construct) the asset | the delivery manager (design/construction) identifies the information they need to operate the asset correctly
Appointing party checklist | Identify the activities that need to be undertaken to work in accordance with ISO 19650 | identify the organisation's policies, plans and procedures to work in accordance with ISO 19650
Responsibility | identify information management responsibility | Identify which organisation is responsible for actives
Level of Information Need (LOIN) | minimum amount of information needed for the appointing party to accept an infromation exchange | What is the minimum amount of information needed to make the required decision at the point of the information exchange
ExampleOIR | examples of information that can be required within an OIR | examples to be considered when writing the OIR
Example Trigger | examples of information that can be required within an AIM | examples to be considered when writing the AIR
Examples AIR | examples of information that can be required within an AIM | examples to be considered when writing the AIR

## OIR
Organizational information requirements
5.2 Organizational information requirements (OIR)
— strategic business operation;
— strategic asset management;
— portfolio planning;
— regulatory duties; or
— policy-making.
Ref | Person (as a) | Activity (I need to) | Purpose (so that)
Tracking Number | For who? | What active needs to be undertaken? | What is the purpose of that activity to the organizations mission.
OIR001 | School Principle | know how many children can be taught in a classroom | I can plan enrolments
OIR002 | Asset operator | operate the asset to safety regulations Part L | the organisation/individual are compliant and avoids prosecution
OIR003 | Asset manager | monitor the warranty details and expiry of warranty periods for each asset | I can plan ahead and ensure that no assets go beyond their warranty period
OIR004 | Asset manager | calculate the financial and resource impact of deviating from plans that might result in a change in asset availability or performance | I calculate the financial impact of deferring the maintenance of the asset
OIR005 | Asset operator | operate the asset safely | I don't put myself or others at risk
OIR006 | Asset operator | operate the asset as it is intended | the asset reaches or exceeds its planned operational lifespan

## AIR
Asset information requirements
5.3 Asset information requirements (AIR)
AIR set out managerial, commercial and technical aspects of producing asset information.
The managerial and commercial aspects should include the information standard and the production methods and procedures to be implemented by the delivery team.
The technical aspects of the AIR specify those detailed pieces of information needed to answer the asset-related OIR.
These requirements should be expressed in such a way that they can be incorporated into asset management appointments to support organizational decision-making.
A set of AIR should be prepared in response to each trigger event during asset operation and where appropriate should also refer to security requirements.
Where there is a supply chain, the AIR received by a lead appointed party can be sub-divided and passed on in any of its own appointments.
AIR received by a lead appointed party can be augmented with its own information requirements.
Across an asset management strategy and plan there can exist several different appointments.
The AIR from all these should form a single coherent and coordinated set of information requirements, sufficient to address all the asset-related OIR.
Level of information need
Ref | Asset break structure | Asset data dictionary | Geometrical information | Alphanumerical information | Documentation
Tracking Number | Uniclass table | Contains | Why and what is the information needed?
AIR001 | Co Complexes | Co_35_10_37 : Hospital complexes | suitable for opertation <URL LINK> | As per the Asset register <URL LINK> | Layout, Speciation
AIR002 | Ss Systems | Ss_70_80_33_35 Hardwired general lighting systems | suitable for opertation <URL LINK> | As per the Asset register <URL LINK> | Schematic, Layout, Data Sheet
https://uniclass.thenbs.com/
Co Complex
En Entities
EF Elements/ functions
SL Spaces/ locations
Ss Systems
Pr Products
Ac Activities

## PIR
project information requirements
5.4 Project information requirements (PIR)
PIR explain the information needed to answer or inform high-level strategic objectives within the appointing party in relation to a particular built asset project. management process.
PIR are identified from both the project management process and the asset
A set of information requirements should be prepared for each of the appointing party’s key decision points during the project.
Repeat clients may develop a generic set of PIR that can be adopted, with or without amendment, on all of their projects.
Ref | Work stage | Delivery milestone/Decision point | Requirement owner | Information requirement | Support information
Tracking Number | What stage is the information required at? | What are the Key decision points when information needed? | Who is responsible for accepting the information and checking its fit for purpose? | What questions need to be answered? | where you can find the information
PIR001 | Public Spending Code | Decision Gate 0 - Approval to proceed | Project Manager | Strategic Assessment Report | as per Public Spending Code A Guide to Evaluating,Planning and Managing Current Expenditure
PIR002 | CWMF - Stage (i) - Feasibility/ Preliminary Design | Project Review 1: Confirm approval for design expenditure | Project Manager | Project Management Structure | as per CWMF GN 1.1
PIR002 | CWMF - Stage (i) - Feasibility/ Preliminary Design | Project Review 1: Confirm approval for design expenditure | Project Manager | Preliminary Project Brief | as per CWMF GN 1.1
PIR002 | CWMF - Stage (i) - Feasibility/ Preliminary Design | Project Review 1: Confirm approval for design expenditure | Project Manager | Preliminary Output | as per CWMF GN 1.1
PIR002 | CWMF - Stage (i) - Feasibility/ Preliminary Design | Project Review 1: Confirm approval for design expenditure | Project Manager | Specification Feasibility Study and Cost Plan | as per CWMF GN 1.1
PIR002 | CWMF - Stage (i) - Feasibility/ Preliminary Design | Project Review 1: Confirm approval for design expenditure | Project Manager | Design Brief | as per CWMF GN 1.1
PIR002 | CWMF - Stage (i) - Feasibility/ Preliminary Design | Project Review 1: Confirm approval for design expenditure | Project Manager | Final Output Specification | as per CWMF GN 1.1
PIR002 | CWMF - Stage (i) - Feasibility/ Preliminary Design | Project Review 1: Confirm approval for design expenditure | Project Manager | Definitive Project Brief | as per CWMF GN 1.1
PIR002 | CWMF - Stage (i) - Feasibility/ Preliminary Design | Project Review 1: Confirm approval for design expenditure | Project Manager | Project Execution Plan | as per CWMF GN 1.1
PIR002 | CWMF - Stage (i) - Feasibility/ Preliminary Design | Project Review 1: Confirm approval for design expenditure | Project Manager | Risk Management Plan | as per CWMF GN 1.1
PIR003 | Public Spending Code | Decision Gate 1 - Approval in Principle | Project Manager | Preliminary Business Case | as per Public Spending Code A Guide to Evaluating,Planning and Managing Current Expenditure
PIR004 | Stage (ii) Design | Project Review 2: Confirm requirements; review procurement strategy | Project Manager | Definitive Procurement Strategy | as per CWMF GN 1.1
PIR004 | Stage (ii) Design | Project Review 2: Confirm requirements; review procurement strategy | Project Manager | Contract Type Proposal | as per CWMF GN 1.1
PIR004 | Stage (ii) Design | Project Review 2: Confirm requirements; review procurement strategy | Project Manager | Project Team Selection Report | as per CWMF GN 1.1
PIR005 | Stage (ii) Design | Project Review 3: Assess project design and Outline Cost Plan | Project Manager | Outline Sketch Scheme (Building) | as per CWMF GN 1.1
PIR005 | Stage (ii) Design | Project Review 3: Assess project design and Outline Cost Plan | Project Manager | Preliminary Planning drawings (C. Eng.) | as per CWMF GN 1.1
PIR005 | Stage (ii) Design | Project Review 3: Assess project design and Outline Cost Plan | Project Manager | Outline Cost Plan | as per CWMF GN 1.1
PIR006 | Stage (ii) Design | Project Review 4: Assess project prior to statutory approval | Project Manager | Developed Sketch Scheme; | as per CWMF GN 1.1
|  |  | Project Manager | Developed Cost Plan; | as per CWMF GN 1.1
|  |  | Project Manager | Statutory Approval Submission | as per CWMF GN 1.1
PIR007 | Stage (ii) Design | Project Review 5: Assess outcome from statutory approval | Project Manager | Developed Cost Plan (reviewed) | as per CWMF GN 1.1
PIR008 | Stage (iii) Tender | Project Review 6: Approve detailed design solution; review pre-tender cost check; review risk | Project Manager | Tender Documentation | as per CWMF GN 1.1
PIR008 | Stage (iii) Tender | Project Review 6: Approve detailed design solution; review pre-tender cost check; review risk | Project Manager | Detailed Pre-tender Cost Check; | as per CWMF GN 1.1
PIR008 | Stage (iii) Tender | Project Review 6: Approve detailed design solution; review pre-tender cost check; review risk | Project Manager | Whole Life Cost Update | as per CWMF GN 1.1
PIR008 | Stage (iii) Tender | Project Review 6: Approve detailed design solution; review pre-tender cost check; review risk | Project Manager | Contractor List Selection | as per CWMF GN 1.1
PIR009 | Public Spending Code | Decision Gate 2 - Pre-Tender Approval | Project Manager | Detailed Project Brief and Procurement Strategy | as per Public Spending Code A Guide to Evaluating,Planning and Managing Current Expenditure
PIR010 | Stage (iii) Tender | Project Review 7: Review tender returns in advance of awarding the contract | Project Manager | Tender Assessment Criteria; | as per CWMF GN 1.1
PIR010 | Stage (iii) Tender | Project Review 7: Review tender returns in advance of awarding the contract | Project Manager | Tender Analysis And Report; | as per CWMF GN 1.1
PIR010 | Stage (iii) Tender | Project Review 7: Review tender returns in advance of awarding the contract | Project Manager | Contractor Recommendation | as per CWMF GN 1.1
PIR011 | Public Spending Code | Decision Gate 3 - Post-Tender Approval | Project Manager | Final Business Case | as per Public Spending Code A Guide to Evaluating,Planning and Managing Current Expenditure
PIR012 | Stages (iv) Construction | implementation/construction process; change control; contract | Project Manager | Various contract management reports | as per CWMF GN 1.1
PIR013 | Public Spending Code | Implementation | Project Manager | Monitoring Reports | as per Public Spending Code A Guide to Evaluating,Planning and Managing Current Expenditure
PIR015 | Stages (v) Handover | Project Review | Project Manager | Project Outturn Review | as per CWMF GN 1.1
PIR016 | Public Spending Code | Project Completion Review | Project Manager | Project Completion Report | as per Public Spending Code A Guide to Evaluating,Planning and Managing Current Expenditure
PIR017 | Public Spending Code | Ex-post Evaluation | Project Manager | Ex-post Evaluation Report (to be published) | as per Public Spending Code A Guide to Evaluating,Planning and Managing Current Expenditure

## Checklist
ISO 19650 Information management process compliance checklist (ISO 19650-1, -2 and -3)
Ref | ISO 19650-12 | ISO 19650-2 | ISO 19650-3 | Activities | Description | Requirement | Documentation | Status | Responsibility
Tracking Number | Concepts and principles | Delivery phase of the assets | Operational phase of the assets | Activities in the standard | Description of the subactivities in the standard | What is required to be compliant with the standard? | Evidence of compliance | status if the organcaiton needs | Why and what is the information needed?
1 |  | 5.1.1. | 5.1.1. | 1 assessment and need | Appoint individuals to undertake the information management function | Outline which nominated individuals from within the appointing party’s organisation has been appointed to undertake the information management function on behalf of the appointing party? | policy, plan, or procedure <URL LINK> | not started | Appointing Party
2 | 5.1 | 5.1.2. | 5.1.2. | 1 assessment and need | Principles Establish the project’s information requirements Establish organizational information requirements | What are the purposes for requiring information deliverables which have been defined, including the aspects of the asset that are intended to be managed? | policy, plan, or procedure <URL LINK> | not started | Appointing Party
3 |  | 5.1.3. | 5.1.3. | 1 assessment and need | Establish the project’s information delivery milestones Identify the assets for which information shall be managed | Has the appointing party established the project’s information delivery milestones in accordance with the project’s plan of work? Where have these milestones been documented? Has the appointing party identified the assets for which information shall be managed? | policy, plan, or procedure <URL LINK> | not started | Appointing Party
4 |  |  | 5.1.4. | 1 assessment and need | Establish the asset information requirements | Has the appointing party established the asset information requirements (AIR) for each asset identified? | policy, plan, or procedure <URL LINK> | not started | Appointing Party
5 |  |  | 5.1.5 | 1 assessment and need | Identify the foreseeable trigger events for which information shall be managed | Has the appointing party identified and recorded foreseeable trigger events, representing those events during the operational phase when new or updated information concerning an asset will be generated or required? (Refer to ISO 19650-3 Annex A.3.) | policy, plan, or procedure <URL LINK> | not started | Appointing Party
6 |  | 5.1.4. | 5.1.6. | 1 assessment and need | Establish the project’s information standard Establish the asset information standard | Has the appointing party established any specific information standards required by the appointing party’s organisation within the project’s information standard? What are the specific information standards? Has the appointing party established any specific information standards required by the appointing party’s organization within the asset information standard? | policy, plan, or procedure <URL LINK> | not started | Appointing Party
7 |  | 5.1.5. | 5.1.7. | 1 assessment and need | Establish the project’s information production methods and procedures Establish the asset information production methods and procedures | What specific information production methods and procedures required have been established by the appointing party within the project’s information production methods and procedures? Has the appointing party established any specific information production methods and procedures required by their organization within the asset information production methods and procedures? | policy, plan, or procedure <URL LINK> | not started | Appointing Party
8 |  | 5.1.6. | 5.1.8. | 1 assessment and need | Establish the project’s reference information and shared resources Establish the reference information and shared resources | What reference information and shared resources has been established by the appointing party that they intend to share with the prospective lead appointed parties during the tender process or appointment, using open data standards whenever possible to avoid duplication of effort and interoperability issues? Has the appointing party established the reference information and resources that they intend to share with the prospective lead appointed parties during the tender process and during the appointment, using open data standards whenever possible to avoid interoperability issues? | policy, plan, or procedure <URL LINK> | not started | Appointing Party
9 |  | 5.1.7. | 5.1.9. | 1 assessment and need | Establish the project’s common data environment Establish the common data environment | Has the appointing party established (i.e. implemented, configured and supported) the project’s common data environment (CDE) to serve the overall requirements of the project and to support the collaborative production of information? Please provide details on the CDE. Has the appointing party established the common data environment (CDE) in accordance with ISO 19650-1:2018, Clause 12? This shall be a combination of workflow and information storage solution to support the information management process for the asset(s). | policy, plan, or procedure <URL LINK> | not started | Appointing Party
10 |  |  | 5.1.10 | 1 assessment and need | Establish links to enterprise systems | If existing enterprise systems are used to store asset information then has the appointing party established or adapted information quality and information security processes within those systems to ensure they comply with the requirements of this document, irrespective of where or how the information is stored? (Refer to ISO 19650-3 Annex A.5) | policy, plan, or procedure <URL LINK> | not started | Appointing Party
11 |  |  | 5.1.11 | 1 assessment and need | Establish the asset information model | Has the appointing party established or reviewed and adapted as necessary the asset information model (AIM) to hold all information specified in AIR related to the asset or assets identified? The AIM shall be a federated information model which can include contents from different information providers (appointed parties)? (Refer to Annex A) | policy, plan, or procedure <URL LINK> | not started | Appointing Party
12 |  |  | 5.1.12 | 1 assessment and need | Establish processes to maintain the AIM | Has the appointing party established or followed existing suitable processes to maintain the AIM for as long as is appropriate? | policy, plan, or procedure <URL LINK> | not started | Appointing Party
13 |  | 5.1.8. | 5.1.13 | 1 assessment and need | Establish the project’s information protocol Establish the asset information protocol | How has the appointing party established the project’s information protocol, including any associated license agreements, which will, subsequently and appropriately, be incorporated into all appointments? Has the appointing party established the asset information protocol to set out the rights and obligations of the appointing party and the appointed parties in relation to the AIM, and incorporated the information protocol into all appointments? | policy, plan, or procedure <URL LINK> | not started | Appointing Party
14 | 5.2 |  | Annex A | 2 invitation to tender (Request to provide service) | Organizational information requirements (OIR) Guidance related to the information management process | Where have the Organisational information requirements (OIR) been defined? | policy, plan, or procedure <URL LINK> | not started | Appointing Party
15 | 5.3 |  |  | 2 invitation to tender (Request to provide service) | Asset information requirements (AIR) | Where have the Asset information requirements (AIR) been defined including: • the information standard • the production methods and procedures to be implemented by the delivery team. • the detailed pieces of information needed to answer the asset-related OIR. | policy, plan, or procedure <URL LINK> | not started | Appointing Party
16 | 5.4 |  |  | 2 invitation to tender (Request to provide service) | Project information requirements (PIR) | How have Project information requirements (PIR) been defined for each of the appointing party’s key decision points during the project? | policy, plan, or procedure <URL LINK> | not started | Appointing Party
17 |  |  | 5.2.1 | 2 invitation to tender (Request to provide service) | Decide the type of activity providing information | Has the appointing party appointed a lead appointed party in relation to each trigger event during the operational phase, including trigger events not originally identified? (Refer to ISO 19650-3 Annex A.3) | policy, plan, or procedure <URL LINK> | not started
18 | 5.5 | 5.2.1 | 5.2.2 | 2 invitation to tender (Request to provide service) | Exchange information requirements (EIR) Establish the appointing party’s exchange information requirements | What exchange information requirements (EIR) has the appointing party established which need to be met by the prospective lead appointed party during the appointment? Has the appointing party established the exchange information requirements for the [EIR (ISO 19650‑3)] necessary to enable it to meet its AIR, and therefore to meet the appropriate OIR for each appointment and trigger event? | policy, plan, or procedure <URL LINK> | not started | Appointing Party
19 | 5.6 |  | Annex A | 2 invitation to tender (Request to provide service) | Asset information model (AIM) Guidance related to the information management process | Has the Asset information model (AIM) been developed? | policy, plan, or procedure <URL LINK> | not started | Appointing Party
20 | 5.7 |  |  | 2 invitation to tender (Request to provide service) | Project information model (PIM) | Has the Project information model (PIM) been developed? | policy, plan, or procedure <URL LINK> | not started | Appointing Party
21 |  | 5.2.2 | 5.2.3 | 2 invitation to tender (Request to provide service) | Assemble reference information and shared resource | Has the appointing party assembled the reference information or shared resources that they intend to provide to the prospective lead appointed party during the tender process or appointment? Provide details on the reference information or shared resources to be provided to the prospective lead appointed party. Has the appointing party assembled the reference information or shared resources that they intend to provide to the prospective lead appointed party during the tender process or as part of the appointment? | policy, plan, or procedure <URL LINK> | not started | Appointing Party
22 |  | 5.2.3 | 5.2.4 | 2 invitation to tender (Request to provide service) | Establish tender response requirements and evaluation criteria Establish response requirements and evaluation criteria | What are the tender response requirements and evaluation criteria established by the appointing party? | policy, plan, or procedure <URL LINK> | not started | Appointing Party
23 |  | 5.2.4 | 5.2.5 | 2 invitation to tender (Request to provide service) | Compile invitation to tender information Compile information for the invitation to tender/request to provide service | What information has the appointing party compiled to be included within the invitation to tender package? | policy, plan, or procedure <URL LINK> | not started | Appointing Party
24 |  | 5.3.1 | 5.3.1 | 5.3 Tender response | Nominate individuals to undertake the information management function Establish the lead appointed party’s EIR (ISO 19650‑3) | Nominate individuals to undertake the information management function |  | not started | Lead Appointed Party
25 |  | 5.3.2 | 5.3.2 | 5.3 Tender response | Establish the delivery team’s (pre-appointment) BIM execution plan | Establish the delivery team’s (pre-appointment) BIM execution plan |  | not started | Lead Appointed Party
26 |  | 5.3.3 | 5.3.3 | 5.3 Tender response | Assess task team capability and capacity | Assess task team capability and capacity |  | not started | Appointed Party
27 |  | 5.3.4 | 5.3.4 | 5.3 Tender response | Establish the delivery team’s capability and capacity | Establish the delivery team’s capability and capacity |  | not started | Lead Appointed Party
28 |  | 5.3.5 | 5.3.5 | 5.3 Tender response | Establish the delivery team’s mobilization plan | Establish the delivery team’s mobilization plan |  | not started | Lead Appointed Party
29 |  | 5.3.6 | 5.3.6 | 5.3 Tender response | Establish the delivery team’s risk register | Establish the delivery team’s risk register |  | not started | Lead Appointed Party
30 |  | 5.3.7 | 5.3.7 | 5.3 Tender response | Compile the delivery team’s response | Compile the delivery team’s tender response |  | not started | Lead Appointed Party
31 |  | 5.4.1 | 5.4.1 | 5.4 Appointment | Confirm the delivery team’s BIM execution plan | Confirm the delivery team’s BIM execution plan |  | not started | Lead Appointed Party
32 |  | 5.4.2 | 5.4.2 | 5.4 Appointment | Establish the delivery team’s detailed responsibility matrix | Establish the delivery team’s detailed responsibility matrix |  | not started | Lead Appointed Party
33 |  | 5.4.3 | 5.4.3 | 5.4 Appointment | Establish the lead appointed party’s exchange information requirements | Establish the lead appointed party’s exchange information requirements |  | not started | Lead Appointed Party
34 |  | 5.4.4 | 5.4.4 | 5.4 Appointment | Establish the task information delivery plan(s) | Establish the task information delivery plan(s) |  | not started | Lead Appointed Party
35 |  | 5.4.5 | 5.4.5 | 5.4 Appointment | Establish the master information delivery plan | Establish the master information delivery plan |  | not started | Lead Appointed Party
36 |  | 5.4.6 | 5.4.6 | 5.4 Appointment | ﻿Complete lead appointed party’s appointment documents | Has the appointing party taken into account of the following, in that they are included within the completed appointment documents for the lead appointed party and managed via change control throughout the duration of the appointment: • the appointing party’s exchange information requirements; • the project’s information standard (including any agreed additions or amendments); • the project’s information protocol (including any agreed additions or amendments); • the delivery team’s BIM Execution plan; and • the delivery team’s MIDP. | policy, plan, or procedure <URL LINK> | not started | Appointing Party
37 |  | 5.4.7 | 5.4.7 | 5.4 Appointment | Complete appointed party’s appointment documents | Has the appointed party completed the appointment documents? | policy, plan, or procedure <URL LINK> | not started | Appointing Party
38 |  | 5.5.1 | 5.5.1 | 5.5 Mobilisation | Mobilize resources | Mobilize resources |  | not started | Lead Appointed Party
39 |  | 5.5.2 | 5.5.2 | 5.5 Mobilisation | Mobilize information technology | Mobilize information technology |  | not started | Lead Appointed Party
40 |  | 5.5.3 | 5.5.3 | 5.5 Mobilisation | Test the project’s information production methods and procedures Test the asset information production methods and procedures | Test the project’s information production methods and procedures |  | not started | Lead Appointed Party
41 |  |  | 5.5.4 | 5.5 Mobilisation | Maintain resources in readiness for a trigger event |  | policy, plan, or procedure <URL LINK> | not started
42 |  | 5.6.1 | 5.6.1 | 5.6 Collaborative production of information | Check availability of reference information and shared resources | Check availability of reference information and shared resources |  | not started | Appointed Party
43 |  | 5.6.2 | 5.6.2 | 5.6 Collaborative production of information | Generate information | Generate information |  | not started | Appointed Party
44 |  | 5.6.3 | 5.6.3 | 5.6 Collaborative production of information | ﻿Undertake quality assurance check | Undertake quality assurance check |  | not started | Appointed Party
45 |  | 5.6.4 | 5.6.4 | 5.6 Collaborative production of information | Review information and approve for sharing | Review information and approve for sharing |  | not started | Appointed Party
46 |  | 5.6.5 | 5.6.5 | 5.6 Collaborative production of information | ﻿Information model review | Information model review |  | not started | Lead Appointed Party
47 |  |  | 5.6.6 | 5.6 Collaborative production of information | Authorize information model for delivery to the appointing party | Information model authorization |  | not started | Lead Appointed Party
48 |  | 5.7.1 | 5.7.1 | 5.7 Information model delivery | Submit information model for lead appointed party authorization Submit information model for appointing party acceptance | Submit information model for lead appointed party authorization |  | not started | Appointed Party
49 |  | 5.7.2 | 5.7.2 | 5.7 Information model delivery | Review and authorize the information model Review and accept the information model | Review and accept the information model |  | not started | Lead Appointed Party
50 |  | 5.7.3 |  | 5.7 Information model delivery | Submit information model for appointing party acceptance | Submit information model for appointing party acceptance |  | not started | Appointed Party
51 |  | 5.7.4 |  | 5.7 Information model delivery | Review and accept the information model | Has the appointing party undertaken a review of the information model in accordance with the project’s information production methods and procedures and accepted the information model? Please provide details on the review of the information model. | policy, plan, or procedure <URL LINK> | not started | Appointing Party
52 |  | 5.8.1 | 5.8.1 | 5.8 Project close-out | Archive the project information model Aggregate an accepted information model into the AIM | What information containers within the project’s common data environment has the appointing party archived in accordance with the project’s information production methods and procedures? The appointing party is responsible for the process to incorporate an accepted information model into its AIM and reconcile that information with the existing contents of the AIM, irrespective of its source. | policy, plan, or procedure <URL LINK> | not started | Appointing Party
53 |  |  | 5.8.2 | 5.8 Project close-out | Review and continue maintenance of the AIM | Has the appointing party reviewed whether the AIM continues to fulfil the requirements of AIM and is being maintained according to the AIM? | policy, plan, or procedure <URL LINK> | not started | Appointing Party
54 |  | 5.8.2 |  | 5.8 Project close-out | Capture lessons learned for future projects | What lessons learned has the appointing party captured during the project and recorded them in a suitable knowledge store, to be called upon by future projects? | policy, plan, or procedure <URL LINK> | not started | Appointing Party

## Responsibility
information management responsibility matrix (ISO 19650-1, -2 and -3)
Key: Information management responsibility matrix template
R - Responsible for undertaking activity / A - Accountable for activity completion / C - Consulted during activity / I - Informed following activity completion
Standards | Activities | Description | Appointing party (Employer/Client) | Third party | Lead appointed party (Design Stage: Lead Design Team or Construction Stage: Main contractor) | Appointed party (Design Stage: Discipline/Specialists Design Teams or Construction Stage: Sub-contractors)
which standard? | Tracking Number | what is the Activities as per ISO19650-2? | What are the duties of the Employer/Client? | What duties have been assigned to a Third party? | What are the duties of the Lead Design Team or Main contractor? | What are the duties of the Discipline/Specialists Design Teams or Sub-contractors?
ISO 19650-1 | 4 | Asset and project information, perspectives and collaborative working | Applicable to ISO 19650-2 and -3 activities
ISO 19650-1 | 4.1 | Principles | Applicable to ISO 19650-2 and -3 activities
ISO 19650-1 | 4.2 | Information management according to the ISO 19650 series | Applicable to ISO 19650-2 and -3 activities
ISO 19650-1 | 4.3 | Information management perspectives | Applicable to ISO 19650-2 and -3 activities
ISO 19650-1 | 5 | Definition of information requirements and resulting information models | Applicable to ISO 19650-2 and -3 activities
ISO 19650-1 | 5.1 | Principles | Applicable to ISO 19650-2 and -3 activities
ISO 19650-1 | 5.2 | Organizational information requirements (OIR) | Applicable to ISO 19650-2 and -3 activities
ISO 19650-1 | 5.3 | Asset information requirements (AIR) | Applicable to ISO 19650-2 and -3 activities
ISO 19650-1 | 5.4 | Project information requirements (PIR) | Applicable to ISO 19650-2 and -3 activities
ISO 19650-1 | 5.5 | Exchange information requirements (EIR) | Applicable to ISO 19650-2 and -3 activities
ISO 19650-1 | 5.6 | Asset information model (AIM) | Applicable to ISO 19650-2 and -3 activities
ISO 19650-1 | 5.7 | Project information model (PIM) | Applicable to ISO 19650-2 and -3 activities
ISO 19650-1 | 6 | The information delivery cycle | Applicable to ISO 19650-2 and -3 activities
ISO 19650-1 | 6.1 | Principles | Applicable to ISO 19650-2 and -3 activities
ISO 19650-1 | 6.2 | Alignment with the asset life cycle | Applicable to ISO 19650-2 and -3 activities
ISO 19650-1 | 6.3 | Setting information requirements and planning for information delivery | Applicable to ISO 19650-2 and -3 activities
ISO 19650-1 | 6.3.1 | General principles | Applicable to ISO 19650-2 and -3 activities
ISO 19650-1 | 6.3.2 | Delivery team provides information for asset owner/operator or client decisions | Applicable to ISO 19650-2 and -3 activities
ISO 19650-1 | 6.3.3 | Information verification and validation at start and end of project stages | Applicable to ISO 19650-2 and -3 activities
ISO 19650-1 | 6.3.4 | Information is drawn from the whole delivery team | Applicable to ISO 19650-2 and -3 activities
ISO 19650-1 | 6.3.5 | Summary of information delivery from project and asset delivery teams | Applicable to ISO 19650-2 and -3 activities
ISO 19650-1 | 7 | Project and asset information management functions | Applicable to ISO 19650-2 and -3 activities
ISO 19650-1 | 7.1 | Principles | Applicable to ISO 19650-2 and -3 activities
ISO 19650-1 | 7.2 | Asset information management functions | Applicable to ISO 19650-2 and -3 activities
ISO 19650-1 | 7.3 | Project information management functions | Applicable to ISO 19650-2 and -3 activities
ISO 19650-1 | 7.4 | Task information management functions | Applicable to ISO 19650-2 and -3 activities
ISO 19650-1 | 8 | Delivery team capability and capacity | Applicable to ISO 19650-2 and -3 activities
ISO 19650-1 | 8.1 | Principles | Applicable to ISO 19650-2 and -3 activities
ISO 19650-1 | 8.2 | Extent of capability and capacity review | Applicable to ISO 19650-2 and -3 activities
ISO 19650-1 | 9 | Information container-based collaborative working | Applicable to ISO 19650-2 and -3 activities
ISO 19650-1 | 10 | Information delivery planning | Applicable to ISO 19650-2 and -3 activities
ISO 19650-1 | 10.1 | Principles | Applicable to ISO 19650-2 and -3 activities
ISO 19650-1 | 10.2 | Timing of information delivery | Applicable to ISO 19650-2 and -3 activities
ISO 19650-1 | 10.3 | Responsibility matrix | Applicable to ISO 19650-2 and -3 activities
ISO 19650-1 | 10.4 | Defining the federation strategy and breakdown structure for information containers | Applicable to ISO 19650-2 and -3 activities
ISO 19650-1 | 11 | Managing the collaborative production of information | Applicable to ISO 19650-2 and -3 activities
ISO 19650-1 | 11.1 | Principles | Applicable to ISO 19650-2 and -3 activities
ISO 19650-1 | 11.2 | Level of information need | Applicable to ISO 19650-2 and -3 activities
ISO 19650-1 | 11.3 | Information quality | Applicable to ISO 19650-2 and -3 activities
ISO 19650-1 | 12 | Common data environment (CDE) solution and workflow | Applicable to ISO 19650-2 and -3 activities
ISO 19650-1 | 12.1 | Principles | Applicable to ISO 19650-2 and -3 activities
ISO 19650-1 | 12.2 | The work in progress state | Applicable to ISO 19650-2 and -3 activities
ISO 19650-1 | 12.3 | The check/review/approve transition | Applicable to ISO 19650-2 and -3 activities
ISO 19650-1 | 12.4 | The shared state | Applicable to ISO 19650-2 and -3 activities
ISO 19650-1 | 12.5 | The review/authorize transition | Applicable to ISO 19650-2 and -3 activities
ISO 19650-1 | 12.6 | The published state | Applicable to ISO 19650-2 and -3 activities
ISO 19650-1 | 12.7 | The archive state | Applicable to ISO 19650-2 and -3 activities
ISO 19650-1 | 13 | Summary of “building information modelling (BIM) according to the ISO 19650 series”
ISO 19650-2 | 1 | Information management process Assessment and need
ISO 19650-2 | 1.1 | Appoint individuals to undertake the information management function | R/A |  | I | I
ISO 19650-2 | 1.2 | Establish the project’s information requirements | R/A |  | I | I
ISO 19650-2 | 1.3 | Establish the project’s information delivery milestones | R/A |  | I | I
ISO 19650-2 | 1.4 | Establish the project’s information standard | R/A |  | I | I
ISO 19650-2 | 1.5 | Establish the project’s information production methods and procedures | R/A |  | C | C
ISO 19650-2 | 1.6 | Establish the project’s reference information and shared resources | R/A |  | I | I
ISO 19650-2 | 1.7 | Establish the project’s common data environment | R/A (Published) |  | R (WIP/Shared) | I
ISO 19650-2 | 1.8 | Establish the project’s information protocol | R/A |  | I | I
ISO 19650-2 | 2 | Information management process Invitation to tender |  |  | I | I
ISO 19650-2 | 2.1 | Establish the appointing party’s exchange information requirements | R/A |  | I | I
ISO 19650-2 | 2.2 | Assemble reference information and shared resources | R/A |  | I | I
ISO 19650-2 | 2.3 | Establish tender response requirements and evaluation criteria | R/A |  | I | I
ISO 19650-2 | 2.4 | Compile invitation to tender information | R/A |  | I | I
ISO 19650-2 | 3 | Information management process Tender response
ISO 19650-2 | 3.1 | Nominate individuals to undertake the information management function | I |  | R/A | C
ISO 19650-2 | 3.2 | Establish the delivery team’s (pre-appointment) BIM execution plan | I |  | R/A | C
ISO 19650-2 | 3.3 | Assess task team capability and capacity | I |  | R/A | C
ISO 19650-2 | 3.4 | Establish the delivery team’s capability and capacity | I |  | R/A | C
ISO 19650-2 | 3.5 | Establish the delivery team’s mobilization plan | I |  | R/A | C
ISO 19650-2 | 3.6 | Establish the delivery team’s risk register | I |  | R/A | C
ISO 19650-2 | 3.7 | Compile the delivery team’s tender response | I |  | R/A | C
ISO 19650-2 | 4 | Information management process Appointment
ISO 19650-2 | 4.1 | Confirm the delivery team’s BIM execution plan | A |  | R | C
ISO 19650-2 | 4.2 | Establish the delivery team’s detailed responsibility matrix | A |  | R | C
ISO 19650-2 | 4.3 | Establish the lead appointed party’s exchange information requirements | A |  | R | C
ISO 19650-2 | 4.4 | Establish the task information delivery plan(s) | A |  | R | C
ISO 19650-2 | 4.5 | Establish the master information delivery plan | A |  | R | C
ISO 19650-2 | 4.6 | ﻿Complete lead appointed party’s appointment documents | A |  | R | C
ISO 19650-2 | 4.7 | Complete appointed party’s appointment documents | A |  | R | C
ISO 19650-2 | 5 | Information management process Mobilization
ISO 19650-2 | 5.1 | Mobilize resources | A |  | R | C
ISO 19650-2 | 5.2 | Mobilize information technology | A |  | R | C
ISO 19650-2 | 5.3 | Test the project’s information production methods and procedures | I |  | R/A | C
ISO 19650-2 | 6 | Information management process Collaborative production of information
ISO 19650-2 | 6.1 | Check availability of reference information and shared resources | I |  | R/A | C
ISO 19650-2 | 6.2 | Generate information | I |  | R/A | C
ISO 19650-2 | 6.3 | ﻿Undertake quality assurance check | I |  | R/A | C
ISO 19650-2 | 6.4 | Review information and approve for sharing | I |  | R/A | C
ISO 19650-2 | 6.5 | ﻿Information model review | I |  | R/A | C
ISO 19650-2 | 7 | Information management process Information model delivery
ISO 19650-2 | 7.1 | Submit information model for lead appointed party authorization | I |  | R/A | C
ISO 19650-2 | 7.2 | Review and authorize the information model | I |  | R/A | C
ISO 19650-2 | 7.3 | Submit information model for appointing party acceptance | I |  | R/A | C
ISO 19650-2 | 7.4 | Review and accept the information model | A |  | R | C
ISO 19650-2 | 8 | Information management process Project close-out
ISO 19650-2 | 8.1 | Archive the project information model | R/A |  | C | C
ISO 19650-2 | 8.2 | Capture lessons learned for future projects | R/A |  | C | C
ISO 19650-3 | 4 | Information management associated with the operational phase of assets
ISO 19650-3 | 4.1 | Information management process associated with the operational phase of assets | R/A |  | C | C
ISO 19650-3 | 4.2 | Relationship between this document and ISO 19650‑2 | R/A |  | C | I
ISO 19650-3 | 5 | Information management process to support the operational phase of assets
ISO 19650-3 | 5.1 | Information management process — assessment and need | R/A |  | C | C
ISO 19650-3 | 1.1 | Appoint individuals to undertake the information management function | R/A |  | C | C
ISO 19650-3 | 1.2 | Establish organizational information requirements | R/A |  | I | I
ISO 19650-3 | 1.3 | Identify the assets for which information shall be managed | R/A |  | I | I
ISO 19650-3 | 1.4 | Establish the asset information requirements | R/A |  | C | C
ISO 19650-3 | 1.5 | Identify the foreseeable trigger events for which information shall be managed | R/A |  | C | C
ISO 19650-3 | 1.6 | Establish the asset information standard | R/A |  | C | C
ISO 19650-3 | 1.7 | Establish the asset information production methods and procedures | R/A |  | C | C
ISO 19650-3 | 1.8 | Establish the reference information and shared resources | R/A |  | C | C
ISO 19650-3 | 1.9 | Establish the common data environment | R/A |  | C | C
ISO 19650-3 | 1.1 | Establish links to enterprise systems | R/A |  | C | C
ISO 19650-3 | 1.11 | Establish the asset information model | R/A |  | C | C
ISO 19650-3 | 1.12 | Establish processes to maintain the AIM | R/A |  | C | C
ISO 19650-3 | 1.13 | Establish the asset information protocol | R/A |  | C | C
ISO 19650-3 | 5.2 | Information management process — Invitation to tender/request to provide service
ISO 19650-3 | 2.1 | Decide the type of activity providing information | R/A |  | I | I
ISO 19650-3 | 2.2 | Establish the appointing party’s exchange information requirements | R/A |  | I | I
ISO 19650-3 | 2.3 | Assemble reference information and shared resources | R/A |  | I | I
ISO 19650-3 | 2.4 | Establish response requirements and evaluation criteria | R/A |  | I | I
ISO 19650-3 | 2.5 | Compile information for the invitation to tender/request to provide service | R/A |  | I | I
ISO 19650-3 | 2.6 | Activities for invitation to tender/request to provide service | R/A |  | I | I
ISO 19650-3 | 5.3 | Information management process — Response to invitation to tender/request to provide service
ISO 19650-3 | 3.1 | Nominate individuals to undertake the information management function | I |  | R/A | C
ISO 19650-3 | 3.2 | Establish the delivery team’s (pre-appointment) BIM execution plan | I |  | R/A | C
ISO 19650-3 | 3.3 | Assess task team capability and capacity | I |  | R/A | C
ISO 19650-3 | 3.4 | Establish the delivery team’s capability and capacity | I |  | R/A | C
ISO 19650-3 | 3.5 | Establish the delivery team’s mobilization plan | I |  | R/A | C
ISO 19650-3 | 3.6 | Establish the delivery team’s risk register | I |  | R/A | C
ISO 19650-3 | 3.7 | Compile the delivery team’s response | I |  | R/A | C
ISO 19650-3 | 5.4 | Information management process — Appointment
ISO 19650-3 | 4.1 | Confirm the delivery team’s BIM execution plan | I |  | R/A | C
ISO 19650-3 | 4.2 | Establish the delivery team’s detailed responsibility matrix | I |  | R/A | C
ISO 19650-3 | 4.3 | Establish the lead appointed party’s EIR (ISO 19650‑3) | I |  | R/A | C
ISO 19650-3 | 4.4 | Establish the task information delivery plan(s) | I |  | R/A | C
ISO 19650-3 | 4.5 | Establish the master information delivery plan | I |  | R/A | C
ISO 19650-3 | 4.6 | Complete lead appointed party’s appointment | I |  | R/A | C
ISO 19650-3 | 4.7 | Complete appointed party’s appointment | I |  | R/A | C
ISO 19650-3 | 5.5 | Information management process — Mobilization
ISO 19650-3 | 5.1 | Mobilize resources | I |  | R/A | C
ISO 19650-3 | 5.2 | Mobilize information technology | I |  | R/A | C
ISO 19650-3 | 5.3 | Test the asset information production methods and procedures | I |  | R/A | C
ISO 19650-3 | 5.4 | Maintain resources in readiness for a trigger event | I |  | R/A | C
ISO 19650-3 | 5.6 | Information management process — Production of information
ISO 19650-3 | 6.1 | Check availability of reference information and shared resources | I |  | R/A | C
ISO 19650-3 | 6.2 | Generate information | I |  | R/A | C
ISO 19650-3 | 6.3 | Undertake quality assurance check | I |  | R/A | C
ISO 19650-3 | 6.4 | Review information and approve for sharing | I |  | R/A | C
ISO 19650-3 | 6.5 | Review information model | I |  | R/A | C
ISO 19650-3 | 5.7 | Information management process — Information model acceptance by appointing party
ISO 19650-3 | 7.1 | Submit information model for appointing party acceptance | R/A |  | I | I
ISO 19650-3 | 7.2 | Review and accept the information model | R/A |  | I | I
ISO 19650-3 | 5.8 | Information management process — AIM aggregation
ISO 19650-3 | 8.1 | Aggregate an accepted information model into the AIM | R/A |  | I | I
ISO 19650-3 | 8.2 | Review and continue maintenance of the AIM | R/A |  | I | I

## LOINeed
Level of information need
11.2 Level of information need
The level of information need of each information deliverable should be determined according to its purpose.
This should include the appropriate determination of quality, quantity and granularity of information. This is referred to as its level of information need and this can vary from deliverable to deliverable.
A range of metrics exist to determine levels of information need. For example, two complementary but independent metrics can define the geometrical and alphanumerical content in terms of quality, quantity and granularity.
Once these metrics have been defined, they should be used to determine the levels of information need across the whole project or asset.
The levels of information need should be determined by the minimum amount of information needed to answer each relevant requirement, including information required by other appointed parties, and no more.
Anything beyond this minimum is considered as waste.
The relevance of an information deliverable is not always correlated to its granularity. Level of information need is, however, closely linked to the federation strategy
The granularity of alphanumerical information should be considered to be at least as important as that of geometrical information.
I.S. EN 17412-1:2020 Building Information Modelling - Level of Information Need - Part 1: Concepts and principles
Level of information need
[5 empty] | Geometrical information |  |  |  |  | Alphanumerical information
Ref | Purpose | Information delivery milestone | Actor | Object | Detail | Dimensionality | Location | Appearance | Parametric behaviour | Alphanumerical information Identification | Alphanumerical information Information content: | Documentation

## ExampleOIR
Examples of activities requiring asset information and example organizational information requirements (ISO 19650-3 A.2)
Organizational views on which activities belong to which group (strategic, tactical, operational) can differ, so the following examples have not been grouped:
Ref | Activities | Description
A.2.1 | strategic, tactical, operational | asset accounting, activity costing, forecasting;
A.2.2 | strategic, tactical, operational | planning and budgeting;
A.2.3 | strategic, tactical, operational | demand management and customer expectation policy;
A.2.4 | strategic, tactical, operational | capital investment and life cycle costing;
A.2.5 | strategic, tactical, operational | innovation and change management;
A.2.6 | strategic, tactical, operational | interfacing with regulatory bodies;
A.2.7 | strategic, tactical, operational | publication of asset information for use by the public;
A.2.8 | strategic, tactical, operational | asset operation or utilization;
A.2.9 | strategic, tactical, operational | asset modifications, refurbishment, replacement, reuse/redeployment, disposal, recycling;
A.2.10 | strategic, tactical, operational | spares, materials and purchasing;
A.2.11 | strategic, tactical, operational | data, information and knowledge management;
A.2.12 | strategic, tactical, operational | contractor and supplier management;
A.2.13 | strategic, tactical, operational | human resources, skills development and competencies;
A.2.14 | strategic, tactical, operational | maintenance, inspection, condition and performance monitoring;
A.2.15 | strategic, tactical, operational | contingency planning and emergencies;
A.2.16 | strategic, tactical, operational | energy efficiency and environmental aspects, for example renewable resources, recycling, waste management, air purity, hygiene;
A.2.17 | strategic, tactical, operational | risk assessment and management; and
A.2.18 | strategic, tactical, operational | ﻿safety, health and environmental management.
A.2.19 | strategic, tactical, operational | Information to support:
A.2.20 | strategic, tactical, operational | the financial benefits of planned improvement activities;
A.2.21 | strategic, tactical, operational | a means to predict the performance of the asset to support operational decision making;
A.2.22 | strategic, tactical, operational | the operational and financial impact of asset unavailability or failure;
A.2.23 | strategic, tactical, operational | the life cycle cost comparisons of alternative capital investments;
A.2.24 | strategic, tactical, operational | expiry dates of warranties;
A.2.25 | strategic, tactical, operational | an assessment of the end of an asset’s economic life, for example when the asset related expenditure exceeds the associated income;
A.2.26 | strategic, tactical, operational | quality targets for the performance of assets;
A.2.27 | strategic, tactical, operational | service levels for asset management and facility management;
A.2.28 | strategic, tactical, operational | the cost of specific activities (activity-based costing), for example the total cost of maintaining a specific asset/asset system;
A.2.29 | strategic, tactical, operational | asset replacement values;
A.2.30 | strategic, tactical, operational | financial analysis of planned income and expenditure;
A.2.31 | strategic, tactical, operational | the financial and resource impact of deviating from plans that can result in a change in asset availability or performance (for example what is the financial impact of deferring the maintenance of a specific generator by six months?);
A.2.32 | strategic, tactical, operational | overall financial performance; and
A.2.33 | strategic, tactical, operational | identification, assessment and control of asset related risks.

## ExampleTrigger
Example trigger events (ISO 19650-3 A.3)
The types of trigger events for which the information management process should be operated will be established by the appointing party (5.1.5). Examples of trigger events include:
Ref | Description
A.3.1 | the organization’s decision to manage information relating to an existing asset according to
A.3.2 | this document;
A.3.3 | performance evaluation of an asset, including failure trends from similar components used
A.3.4 | elsewhere and experience-based learning and feedback from asset performance;
A.3.5 | inspection of an asset;
A.3.6 | maintenance work on an asset, whether planned or reactive;
A.3.7 | minor works on an asset, such as minor repairs, component replacements or minor upgrades;
A.3.8 | initiating a project to deliver a new asset;
A.3.9 | major works on an existing asset such as major repairs, refurbishments or major upgrades;
A.3.10 | creation of a new asset;
A.3.11 | ﻿asset replacement;
A.3.12 | end-of-life works, such as decommissioning, demolition or deactivation and preservation;
A.3.13 | planning for and, where appropriate, implementing an emergency response;
A.3.14 | risk assessment of an asset;
A.3.15 | change in value of an asset;
A.3.16 | change in regulations applying to an asset;
A.3.17 | change in information demanded by an appropriate regulator;
A.3.18 | change in organizational requirements relating to the asset, for example change of operating parameters or conditions;
A.3.19 | change in ownership of an asset;
A.3.20 | change in operator of an asset; and
A.3.21 | change in maintainer of an asset.

## ExampleAIR
Examples of information that can be required within an AIM (ISO 19650-3 A.4)
The following are examples of information that can be required within an AIM to support OIR:
Ref | Activities | Description
A.4.1 | Managerial information | unique asset identifiers;
A.4.1 | Managerial information | locations of the assets, possibly using spatial referencing or geographical information systems;
A.4.1 | Managerial information | spatial data relating to assets, for example pavement areas, room sizes;
A.4.1 | Managerial information | warranties and guarantee periods;
A.4.1 | Managerial information | access planning and work schedules;
A.4.1 | Managerial information | historical record of proactive and reactive maintenance tasks performed;
A.4.1 | Managerial information | future schedule of maintenance and inspection tasks including details of overdue tasks, and including details of the maintenance organization and details of qualifications/certifications required to carry out each task;
A.4.1 | Managerial information | asset related standards, process(es) and procedure(s);
A.4.1 | Managerial information | the presence of any hazardous contents or waste;
A.4.1 | Managerial information | details of asset destination at end of current life;
A.4.1 | Managerial information | details of emergency plans including responsibilities and contact details; and
A.4.1 | Managerial information | details of historical asset failures, causes and consequences (if known).
A.4.2 | Technical information | engineering data and design parameters;
A.4.2 | Technical information | details of technical dependencies and interdependencies of assets;
A.4.2 | Technical information | commissioning dates and data; and
A.4.2 | Technical information | operational data including performance characteristics and design limits.
A.4.3 | Legal information | details of ownership and maintenance demarcation where assets interface across a system or network of assets;
A.4.3 | Legal information | work instructions together with diagrams and reporting requirements, legal obligations such as health and safety file information, and safety/environmental considerations;
A.4.3 | Legal information | asset related contractual information; and
A.4.3 | Legal information | task risk assessments and control measures.
A.4.4 | Commercial information | descriptions of assets and the asset systems they serve;
A.4.4 | Commercial information | functions of assets, including any interdependencies to the activities that require them;
A.4.4 | Commercial information | vendor data (details of the organization that supplied the asset) including asset lead time;
A.4.4 | Commercial information | the condition and duty of assets including intensity of use;
A.4.4 | Commercial information | key performance indicators;
A.4.4 | Commercial information | condition and performance targets or standards;
A.4.4 | Commercial information | criteria of non-conformance and the actions to be taken;
A.4.4 | Commercial information | the criticality of assets and spaces to the organization; and
A.4.4 | Commercial information | identities and levels of spares held, inter-changeability, specifications and storage locations.
A.4.5 | Financial information | whole life costs of asset deployment including cost of historical and planned maintenance tasks;
A.4.5 | Financial information | operating costs;
A.4.5 | Financial information | downtime impact;
A.4.5 | Financial information | current asset replacement value; and
A.4.5 | Financial information | original purchase/leasing costs.