## Instruction
Document information
Title | Guidance | Information
Project | What Project is the Plan for? | Project Name
Title | What is the title of this document? | Information Management Plan - Appointing Party
Quality | Who performed the quality check on this document? | Checked PL / Reviewed PL / Approved PL
Document File Naming | What is this document's file naming? | InformationManagementPlan-AppointingParty.xlsx
Version | What is this document's current version? | A01.01 - 19/12/2023
Template Instructions
Colour and font | Guidance | Example
sentence in grey italics | This represents what is required as a response in plain language | Why and what is the information needed?
red italics | This represents guidance on completing the document | Add Hyperlink
red | This represents an example of suitable text | Fire Safety Certificate Report
Tables | Purpose | Response required
hyperlink to the relevant table | Why this information is needed? | What the tenderer must understand from the information?
Responsibility (Information Management) | identify which parties are responsible for Information Management tasks or duties | the lead appointed party tenderer are expected to understand the scope of their work under the contract
EIR (Exchange Information Requirements) | defines exchanges expected by the appointing party as part of the contract | the lead appointed party tenderer is expected to understand what, when, how information is produced and for whom the information is needed
Supporting information | identify existing information which could be used or referred to by the lead appointed party | the lead appointed party tenderer is expected to understand what information is available to them to use
Acceptance criteria | identify how the information should be created/ managed(shared)/ presented | the lead appointed party tenderer is expected to understand how the information is to be accepted by the appointing party and what methodologies the appointing party expect the lead appointed party tenderer to prepare
Evaluation criteria | identify the weighting used when the tender response is evaluated | understand how the tender return will be scored
Glossary | ISO 19650 definition | CWMF terms
ISO 19650 terms in the documentation | What is the ISO 19650 definition for the term? | what is the CWMF equivalent
Appointing party | An individual or organisation – often referred to as the client – who commissions others (Lead Appointed Parties) to undertake a specific task and, in undertaking that task, to provide information relating to that task. | Employer/Client/Contracting Authority
Third party | identify which parties are responsible for Information Management tasks or duties | Third party
Lead appointed party | The individual or organisation appointed to be accountable for delivery of agreed (often contracted) information deliverables at defined exchange points. | Design Stage: Lead Design Team or Construction Stage: Main contractor
Appointed party | An individual or organisation who is commissioned to undertake a specific task and, in undertaking that task, to provide information relating to that task. | Design Stage: Discipline/Specialists Design Teams or Construction Stage: Sub-contractors)
Further ISO 19650 definition | https://www.ukbimframework.org/wp-content/uploads/2023/06/GIIG-Glossary_V3.pdf
Further CWMF definition | https://constructionprocurement.gov.ie/wp-content/uploads/GL1-Glossary-v1.0-28-7-09.pdf

## Responsibility
Information management responsibility matrix
Table A.1 — Information management responsibility matrix template
Key: Information management responsibility matrix template
R - Responsible for undertaking activity / A - Accountable for activity completion / C - Consulted during activity / I - Informed following activity completion
Index | Activities | Activities Description | Table | Appointing party (Employer/Client) | Third party | Lead appointed party (Design Stage: Lead Design Team or Construction Stage: Main contractor) | Appointed party (Design Stage: Discipline/Specialists Design Teams or Construction Stage: Sub-contractors)
1 | Tracking Number | what is the Activities as per ISO19650-2? | Where the information is in this plan. | What are the duties of the Employer/Client? | What duties have been assigned to a Third party? | What are the duties of the Lead Design Team or Main contractor? | What are the duties of the Discipline/Specialists Design Teams or Sub-contractors?
1 | 1 | Information management process Assessment and need
2 | 1.1 | Appoint individuals to undertake the information management function | Functions (Information Management) | R/A |  | I | I
3 | — | the tasks that the prospective lead appointed party or third party will be responsible for;
4 | — | ﻿the authority that the appointing party will delegate to the prospective lead appointed party or third party; and
5 | — | the competency (knowledge or skills) that the individuals undertaking the function will need.
6 | 1.2 | Establish the project’s information requirements | EIR (Exchange Information Requirements) | R/A |  | I | I
7 | — | the project scope;
8 | — | the intended purpose for which the information will be used by the appointing party;
9 | — | the project plan of work;
10 | — | the intended procurement route;
11 | — | the number of key decision points throughout the project;
12 | — | the decisions that the appointing party needs to make at each key decision point; and
13 | — | the questions to which the appointing party needs answers, to make informed decisions.
14 | 1.3 | Establish the project’s information delivery milestones | EIR (Exchange Information Requirements) | R/A |  | I | I
15 | — | the appointing party’s key decision points;
16 | — | its own information delivery obligations (if any);
17 | — | the nature and substance of information to be delivered at each key decision point; and
18 | — | the date(s) relative to each key decision point that the information model is to be delivered.
19 | 1.4 | Establish the project’s information standard | Supporting information | R/A |  | I | I
20 | a) | the exchange of information:
21 | — | within the appointing party’s organization,
22 | — | between the appointing party and external stakeholders,
23 | — | between the appointing party and external operators or maintainers,
24 | — | between the prospective lead appointed party and the appointing party,
25 | — | ﻿between prospective appointed parties on the same project, and
26 | — | between interdependent projects;
27 | b) | the means of structuring and classifying information;
28 | c) | the method of assignment for level of information need; and
29 | d) | the use of information during the operational phase of the asset.
30 | 1.5 | Establish the project’s information production methods and procedures | Acceptance Criteria | R/A |  | C | C
31 | a) | the capture of existing asset information;
32 | b) | the generation, review or approval of new information;
33 | c) | the security or distribution of information; and
34 | d) | the delivery of information to the appointing party.
35 | 1.6 | Establish the project’s reference information and shared resources | Supporting information | R/A |  | I | I
36 | a) | existing asset information:
37 | — | from within the appointing party’s organization;
38 | — | from adjacent asset owners (utility companies, etc.);
39 | — | under license from external providers (mapping and imagery, etc.); and
40 | — | within public libraries and other sources of historical records.
41 | b) | shared resources, for example:
42 | — | process output templates (BIM execution plan, master information delivery plan, etc.);
43 | — | information container templates (2D/3D geometrical models, documents, etc.);
44 | — | style libraries (lines, text and hatch, etc.); or
45 | — | object libraries (2D symbols, 3D objects, etc.).
46 | c) | library objects defined within national and regional standards.
47 | 1.7 | Establish the project’s common data environment | IT Resources | R/A (ClientShared/ Published) |  | R (WIP/Shared) | I
48 | ﻿a) | ﻿each information container to have a unique ID, based upon an agreed and documented convention comprised of fields separated by a delimiter;
49 | b) | each field to be assigned a value from an agreed and documented codification standard;
50 | c) | each information container to have the following attributes assigned:
51 | — | status (suitability);
52 | — | revision;
53 | — | classification (in accordance with the framework defined in ISO 12006-2);
54 | d) | the ability for information containers to transition between states;
55 | e) | the recording of the name of user and date when information container revisions transition between each state; and
56 | f) | controlled access at an information container level.
57 | 1.8 | Establish the project’s information protocol | Acceptance Criteria | R/A |  | I | I
58 | — | specific obligations of the appointing party, prospective lead appointed parties and prospective appointed parties relating to the management or production of information, including the use of the project’s common data environment;
59 | — | any warranties or liabilities associated to the project information model;
60 | — | background and foreground intellectual property rights of information;
61 | — | the use of existing asset information;
62 | — | the use of shared resources;
63 | — | the use of information during the project, including any associated licensing terms; and
64 | — | the re-use of information following the appointment or in the event of termination.
65 | 2 | Information management process Invitation to tender |  |  |  | I | I
66 | 2.1 | Establish the appointing party’s exchange information requirements | EIR (Exchange Information Requirements) | R/A |  | I | I
67 | a) | establish the appointing party’s information requirements to be served during the appointment, and in doing so shall consider their:
68 | — | organizational information requirements,
69 | — | asset information requirements, and
70 | — | project information requirements;
71 | b) | establish the level of information need required to meet each information requirement;
72 | c) | establish the acceptance criteria for each information requirement, and in doing so shall consider:
73 | — | the project’s information standard,
74 | — | the project’s information production methods and procedures, and
75 | — | the use of reference information or shared resources provided by the appointing party;
76 | ﻿d) | ﻿establish the supporting information that the prospective lead appointed party might need, to fully understand or evaluate each information requirement or its acceptance criteria, and in doing so shall consider:
77 | — | existing asset information,
78 | — | shared resources,
79 | — | supporting documents or guidance material,
80 | — | references to relevant international, national or industry standards, and
81 | — | exemplars of similar information deliverables;
82 | e) | establish the dates, relative to the project’s information delivery milestones and appointing party’s key decision points, that each requirement has to be met, and in doing so shall consider:
83 | — | the time needed by the appointing party to review and accept information, and
84 | — | the appointing party’s internal assurance processes.
85 | 2.2 | Assemble reference information and shared resources | Supporting information | R/A |  | I | I
86 | — | reference information or shared resources identified during project initiation;
87 | — | information generated during previous stages of the project; and
88 | — | the suitability for which the information can be used by the prospective lead appointed party.
89 | 2.3 | Establish tender response requirements and evaluation criteria | Acceptance Criteria | R/A |  | I | I
90 | — | the contents of the delivery team’s (pre-appointment) BIM execution plan;
91 | — | the competency of the prospective individuals undertaking the information management function on behalf of the delivery team;
92 | — | the prospective lead appointed party’s assessment of the delivery team’s capability and capacity;
93 | — | the delivery team’s proposed mobilization plan; and
94 | — | the delivery team’s information delivery risk assessment.
95 | 2.4 | Compile invitation to tender information |  | R/A |  | I | I
96 | — | ﻿the appointing party’s exchange information requirements;
97 | — | the relevant reference information and shared resources (within the project’s common data environment);
98 | — | the tender response requirements and evaluation criteria (if applicable);
99 | — | the project information delivery milestones;
100 | — | the project’s information standard;
101 | — | the project’s information production methods and procedure; and
102 | — | the project’s information protocol.
103 | 3 | Information management process Tender response
104 | 3.1 | Nominate individuals to undertake the information management function | Functions (Information Management) | I |  | R/A | C
105 | — | the appointing party’s exchange information requirements;
106 | — | the tasks that the prospective appointed party or third party will be responsible for;
107 | — | the authority that the prospective lead appointed party will delegate to the prospective appointed party or third party;
108 | — | ﻿the competency (knowledge or skills) that the individuals undertaking the function will need; and
109 | — | probity arrangements if potential conflicts of interest may arise.
110 | 3.2 | Establish the delivery team’s (pre-appointment) BIM execution plan | BEP (BIM execution plan) | I |  | R/A | C
111 | a) | the proposed names and professional résumés of the individuals who will undertake the information management function on behalf of the delivery team;
112 | b) | the delivery team’s information delivery strategy, containing:
113 | — | the delivery team’s approach to meeting the appointing party’s exchange information requirements,
114 | — | a set of objectives/goals for the collaborative production of information,
115 | — | an overview of the delivery team’s organizational structure and commercial relationships, and
116 | — | an overview of the delivery team’s composition, in the form of one or more task teams;
117 | c) | the proposed federation strategy to be adopted by the delivery team;
118 | d) | the delivery team’s high-level responsibility matrix, containing the allocated responsibility for each element of the information model and the key deliverables associated to each element;
119 | e) | any proposed additions or amendments to the project’s information production methods and procedures that the delivery team require to facilitate the effective:
120 | — | capture of existing asset information,
121 | — | generation, review, approval and authorization of information,
122 | — | security and distribution of information, and
123 | — | delivery of information to the appointing party;
124 | f) | any proposed additions or amendments to the project’s information standard that the delivery team require to facilitate the effective:
125 | — | exchange of information between task teams,
126 | — | distribution of information to external parties, or
127 | — | delivery of information to the appointing party;
128 | g) | a proposed schedule of software (including versions), hardware and IT infrastructure the delivery team intend to adopt.
129 | 3.3 | Assess task team capability and capacity | Capability and Capacity | I |  | R/A | C
130 | ﻿a) | ﻿the task team’s capability and capacity to manage information, based upon:
131 | — | the relevant experience and number of task team members who have managed information in accordance with the proposed information delivery strategy; and
132 | — | the relevant education and training available to task team members;
133 | b) | the task team’s capability and capacity to produce information, based upon:
134 | — | the relevant experience and number of task team members who have produced information in accordance with the project’s information production methods and procedures; and
135 | — | the relevant education and training available to task team members;
136 | c) | the availability of information technology (IT) within the task team, based upon:
137 | — | the proposed IT schedule;
138 | — | the specification and quantity of the task team’s hardware;
139 | — | the architecture, maximum capacity and current utilization of the task team’s IT infrastructure; and
140 | — | the associated support and service level agreements available to the task team.
141 | 3.4 | Establish the delivery team’s capability and capacity | Capability and Capacity | I |  | R/A | C
142 | 3.5 | Establish the delivery team’s mobilization plan | Mobilization Plan | I |  | R/A | C
143 | — | testing and documenting the proposed information production methods and procedures;
144 | — | testing the information exchanges between task teams;
145 | — | testing the information delivery to the appointing party;
146 | — | configuring and testing the project’s CDE in accordance with 7;
147 | — | configuring and testing the delivery team’s (distribute CDE and its connectivity to the project CDE (if applicable accordance with 7;
148 | — | procuring, implementing, configuring and testing additional software, hardware and IT infrastructure;
149 | — | developing additional shared resources to be used by the delivery team;
150 | — | developing and delivering education (knowledge require to delivery team members;
151 | — | developing and delivering training (skills require to the delivery team members;
152 | — | recruiting additional members of the delivery team to achieve the required capacity; and
153 | — | ﻿supporting individuals and organizations that join the delivery team during the appointment.
154 | 3.6 | Establish the delivery team’s risk register | Risk Register (Information Management) | I |  | R/A | C
155 | — | assumptions the delivery team has made in relation to the appointing party’s exchange information requirements;
156 | — | meeting the appointing party’s project information delivery milestones;
157 | — | the contents of the project’s information protocol;
158 | — | achieving the proposed information delivery strategy;
159 | — | adopting the project’s information standard and information production methods and procedures;
160 | — | inclusion (or non-inclusion) of proposed amendments to the project’s information standard; and
161 | — | the mobilization of the delivery team to achieve the required capability and capacity.
162 | 3.7 | Compile the delivery team’s tender response |  | I |  | R/A | C
163 | — | (pre-appointment) BIM execution plan (2);
164 | — | capability and capacity assessment summary (4);
165 | — | mobilization plan (5); and
166 | — | information delivery risk assessment (6).
167 | 4 | Information management process Appointment
168 | 4.1 | Confirm the delivery team’s BIM execution plan | BEP (BIM execution plan) | I |  | R/A | C
169 | a) | confirm the names of the individual(s) who will undertake the information management function within the delivery team;
170 | b) | update the delivery team’s information delivery strategy (as required);
171 | c) | update the delivery team’s high-level responsibility matrix (as required);
172 | d) | confirm and document the delivery team’s proposed information production methods and procedures;
173 | e) | agree with the appointing party any additions or amendments to the project’s information standard; and
174 | f) | confirm the schedule of software, hardware and IT infrastructure the delivery team will use.
175 | 4.2 | Establish the delivery team’s detailed responsibility matrix | Information Delivery Plan | I |  | R/A | C
176 | — | what information is to be produced;
177 | — | ﻿when the information is to be exchanged and with whom; and
178 | — | which task team is responsible for its production.
179 | — | the information delivery milestones;
180 | — | the high-level responsibility matrix;
181 | — | the project’s information production methods and procedures;
182 | — | the elements of information container breakdown structure allocated to each task team; and
183 | — | the dependencies on the information production process.
184 | 4.3 | Establish the lead appointed party’s exchange information requirements |  | I |  | R/A | C
185 | a) | define each information requirement, and in doing so shall consider:
186 | — | the appointing party’s information requirements, which the lead appointed party requires the appointed party to meet, and
187 | — | any additional information requirements that the lead appointed party requires the appointed party to meet;
188 | b) | establish the level of information need required to meet each information requirement;
189 | c) | establish the acceptance criteria for each information requirement, and in doing so shall consider:
190 | — | the project’s information standard,
191 | — | the project’s information production methods and procedures, and
192 | — | the use of reference information or shared resources provided by the appointing party or lead appointed party;
193 | d) | establish the dates that need to be met for each requirement, relative to the project’s information delivery milestones, and in doing so shall consider:
194 | — | the time needed by the lead appointed party to review and authorize information, and
195 | — | the lead appointed party’s internal assurance processes;
196 | e) | establish the supporting information that the appointed party might need, to fully understand or evaluate each information requirement or its acceptance criteria, and in doing so shall consider:
197 | — | existing asset information,
198 | — | shared resources,
199 | — | supporting documents or guidance material,
200 | — | references to relevant international, national or industry standards, and
201 | — | ﻿exemplars of similar information deliverables.
202 | 4.4 | Establish the task information delivery plan(s) | Information Delivery Plan | I |  | R/A | C
203 | — | the project’s information delivery milestones;
204 | — | the task team’s responsibilities within the detailed responsibility matrix;
205 | — | the lead appointed party’s information requirements;
206 | — | the availability of shared resources within the delivery team; and
207 | — | the time the task team will need to produce (generate, coordinate, review and approve information.
208 | — | the name and title;
209 | — | the predecessors or dependencies;
210 | — | the level of information need;
211 | — | the (estimate production duration;
212 | — | the information author responsible for its production; and
213 | — | the delivery milestones.
214 | 4.5 | Establish the master information delivery plan | Information Delivery Plan | I |  | R/A | C
215 | — | the assigned responsibilities within the detailed responsibility matrix;
216 | — | the information predecessors or dependencies on information between task teams;
217 | — | the time the lead appointed party will need to review and authorize the information model; and
218 | — | the time the appointing party will need to review and accept the information model.
219 | — | baseline the deliverables and dates within the MIDP;
220 | — | inform each task team and notify if any changes are required to the TIDP; and
221 | — | inform the appointing party of any risks or issues which could impact on the project’s information delivery milestones.
222 | 4.6 | ﻿Complete lead appointed party’s appointment documents |  | I |  | R/A | C
223 | — | the appointing party’s exchange information requirements;
224 | — | the project’s information standard (including any agreed additions or amendments);
225 | — | the project’s information protocol (including any agreed additions or amendments);
226 | — | the delivery team’s BIM Execution plan; and
227 | — | the delivery team’s MIDP.
228 | 4.7 | Complete appointed party’s appointment documents |  | I |  | R/A | C
229 | — | the lead appointed party’s exchange information requirements;
230 | — | the project’s information standard (including any agreed additions or amendments) (see 4);
231 | — | the project’s information protocol (including any agreed additions or amendments);
232 | — | the delivery team’s BIM Execution plan; and
233 | — | the agreed TIDP.
234 | 5 | Information management process Mobilization
235 | 5.1 | Mobilize resources | Mobilization Plan | I |  | R/A | C
236 | — | confirm the resource availability of each task team;
237 | — | develop and deliver education on topics such as the project’s scope, exchange information requirements and delivery milestones (knowledge require to delivery team members; and
238 | — | develop and deliver training (skills require to the delivery team members.
239 | 5.2 | Mobilize information technology | IT Resources | I |  | R/A | C
240 | — | procure, implement, configure and test software, hardware and IT infrastructure (as required);
241 | — | configure and test the project’s CDE in accordance with 7;
242 | — | configure and test the delivery team’s (distribute CDE and its connectivity to the project CDE (if applicable in accordance with 7;
243 | — | test the information exchanges between task teams; and
244 | — | test the information delivery to the appointing party.
245 | 5.3 | Test the project’s information production methods and procedures | Acceptance Criteria | I |  | R/A | C
246 | — | test and document the project’s information production methods and procedures;
247 | — | refine and verify the proposed information container breakdown structure is workable;
248 | — | develop shared resources to be used by the delivery team; and
249 | — | communicate the project’s information production methods and procedures to all tasks teams.
250 | 6 | Information management process Collaborative production of information
251 | 6.1 | Check availability of reference information and shared resources | Supporting information | I |  | R/A | C
252 | 6.2 | Generate information | Acceptance Criteria | I |  | R/A | C
253 | a) | generate information:
254 | — | in compliance with the project’s information standard, and
255 | — | in accordance with the project’s information production methods and procedures;
256 | b) | not generate information that:
257 | — | exceeds the required level of information need,
258 | — | extends beyond the allocated element of the information container breakdown structure,
259 | — | duplicates information generated by other task teams, or
260 | — | contains superfluous detail;
261 | c) | coordinate and cross-reference all information with information shared within the project’s common data environment, in accordance with the project’s information production methods and procedures; and
262 | d) | spatially coordinate geometrical models with other geometrical models shared with the appropriate suitability, residing within the project’s common data environment.
263 | 6.3 | ﻿Undertake quality assurance check | Acceptance Criteria | I |  | R/A | C
264 | a) | if the check is successful:
265 | — | mark the information container as checked, and
266 | — | record the outcome of the check; or
267 | b) | if the check is unsuccessful:
268 | — | reject the information container, and
269 | — | inform the information author of the outcome and corrective action required.
270 | 6.4 | Review information and approve for sharing | Acceptance Criteria | I |  | R/A | C
271 | — | the lead appointed party’s information requirements;
272 | — | the level of information need; and
273 | — | information needed for coordination by other task teams.
274 | a) | if the review is successful:
275 | — | assign the suitability for which the information contained within the information container can be used, and
276 | — | approve the information container for sharing;
277 | b) | if the review is unsuccessful:
278 | — | record why the review was unsuccessful,
279 | — | record any amendments for the task team to complete, and
280 | — | reject the information container.
281 | 6.5 | ﻿Information model review | Acceptance Criteria | I |  | R/A | C
282 | — | the appointing party’s information requirements and acceptance criteria; and
283 | — | the information containers listed within the master information delivery plan.
284 | 7 | Information management process Information model delivery
285 | 7.1 | Submit information model for lead appointed party authorization | Deliverables Schedule | I |  | R/A | C
286 | 7.2 | Review and authorize the information model | Deliverables Schedule | I |  | R/A | C
287 | — | the deliverables listed in the master information delivery plan;
288 | — | the appointing party’s exchange information requirements;
289 | — | the lead appointed party’s exchange information requirements;
290 | — | the acceptance criteria for each information requirement; and
291 | — | the level of information need for each information requirement.
292 | 7.3 | Submit information model for appointing party acceptance | Deliverables Schedule | I |  | R/A | C
293 | 7.4 | Review and accept the information model | Deliverables Schedule | I |  | R/A | C
294 | — | the deliverables listed in the master information delivery plan;
295 | — | the appointing party’s exchange information requirements;
296 | — | the acceptance criteria for each information requirement; and
297 | — | the level of information need for each information requirement.
298 | 8 | Information management process Project close-out
299 | 8.1 | Archive the project information model | IT Resources | R/A | C | C | C
300 | — | which information containers will be needed as part of the asset information model;
301 | — | future access requirements;
302 | — | future re-use; and
303 | — | relevant retention policies to be applied.
304 | 8.2 | Capture lessons learned for future projects |  | R/A | C | C | C

## EIR
Exchange information requirements
2.1 Establish the appointing party’s exchange information requirements
a) establish the appointing party’s information requirements to be served during the appointment, and in doing so shall consider their:
— organizational information requirements,
— asset information requirements, and
— project information requirements;
b) establish the level of information need required to meet each information requirement;
c) establish the acceptance criteria for each information requirement, and in doing so shall consider:
— the project’s information standard,
— the project’s information production methods and procedures, and
— the use of reference information or shared resources provided by the appointing party;
d) establish the supporting information that the prospective lead appointed party might need, to fully understand or evaluate each information requirement or its acceptance criteria, and in doing so shall consider:
— existing asset information,
— shared resources,
— supporting documents or guidance material,
— references to relevant international, national or industry standards, and
— exemplars of similar information deliverables;
e) establish the dates, relative to the project’s information delivery milestones and appointing party’s key decision points, that each requirement has to be met, and in doing so shall consider:
— the time needed by the appointing party to review and accept information, and
— the appointing party’s internal assurance processes.
EIR Ref | Requirement owner | Information requirement description | Level of information need | Acceptance criteria Project’s information standard, project’s information production methods and procedures, and reference information or shared resources | Supporting information Existing asset information, shared resources, supporting documents or guidance material, references to relevant international, national or industry standards, and exemplars of similar information deliverables | Exchange date or frequency
Why and what is the information needed? | who | What is the information that needs to be exchanged? | What content and/or detail is expected for the information to be accepted? | What format/presentation is expected for the information to be accepted? | What information should be considered in the production of the exchange information? | when is the information expected?
EIR-01 | Project Manager | Coordinated cross-disciplinary models. | level of information need <URL LINK> | Acceptance criteria <URL LINK> | existing Topographical survey <URL LINK> | Deliverable at stage completions (all stages) Exchange every 2 weeks starting from (DD-MM-YYYY)
EIR-02 | Project Manager | Geospatial coordinated layout 2D plans, sections, elevations, and details derived for a 3D coordinated model | level of information need <URL LINK> | Acceptance criteria <URL LINK> | existing Asset Models <URL LINK> | Stage completions (all stages)
EIR-03 | Project Manager | Capture of existing Information. Site plan or model with information on altitudes etc. Information on existing infrastructure with associated data. National regulations, municipal by-laws, project site information etc. | level of information need <URL LINK> | Acceptance criteria <URL LINK> | existing Asset Models <URL LINK> | Deliverable at outline design stage completion First exchange DD-MM-YYYY
EIR-04 | Project Manager | Cost Driven Design. Cost report | level of information need <URL LINK> | Acceptance criteria <URL LINK> | The supporting document outlining the objective of target value design as part of the key purposes of using BIM is available on the CDE as background information <URL LINK> | Every second Monday through the design stages of the project. First exchange DD-MM-YYYY
EIR-05 | Project Manager | Commissioning report Document building and information is according to technical specification | level of information need <URL LINK> | Acceptance criteria <URL LINK> | Technical specification <URL LINK> | 14 days before handover DD-MM-YYYY
EIR-06 | Asset Manager | Handover information - As built Attributes for all products used in the installed system defined in the template spreadsheet. Accurate information that represents the physical asset. Model and section and plan drawings generated from this model to reflect the final design. Any information within the model to be coordinated with the record information. | level of information need <URL LINK> | Acceptance criteria <URL LINK> | Technical specification <URL LINK> | 14 days before handover DD-MM-YYYY
EIR-07 | Asset Manager | Handover information - Documentation Provide all instructions, manuals and other information needed to facilitate and operate the building and its technical systems and products safely and according to the technical specification. | level of information need <URL LINK> | Verification routines will check for incomplete field and broken relationships. The properties from the Asset data templates will be checked against the COBie spreadsheet. | Spreadsheet template <INSERT LINK> Asset data templates <INSERT LINK> Sheet template <INSERT LINK> | 28 days before handover

## Acceptance criteria
Acceptance criteria
2.1. c) establish the acceptance criteria for each information requirement, and in doing so shall consider:
— the project’s information standard,
— the project’s information production methods and procedures, and
— the use of reference information or shared resources provided by the appointing party;
1.4 Establish the project’s information standard
a) the exchange of information:
— within the appointing party’s organization,
— between the appointing party and external stakeholders,
— between the appointing party and external operators or maintainers,
— between the prospective lead appointed party and the appointing party,
— between prospective appointed parties on the same project, and
— between interdependent projects;
b) the means of structuring and classifying information;
c) the method of assignment for level of information need; and
d) the use of information during the operational phase of the asset.
1.5 Establish the project’s information production methods and procedures
a) the capture of existing asset information;
b) the generation, review or approval of new information;
c) the security or distribution of information; and
d) the delivery of information to the appointing party.
Purpose | Project’s information standard | Symbol | Value
Units | Units | mm | millimeters
Units | Site Units | m | meters
Units | Currency Unit | € | Euro
Units | ITM cordinators | ITM | Irish Transverse Mercator
Coordinators | Project origin
Coordinators | Survey Point
Purpose | Project’s information standard | Version | Title/Clause
exchange of information within the appointing party’s organization,
exchange of information between the appointing party and external stakeholders,
exchange of information between the appointing party and external operators or maintainers
exchange of information between the prospective lead appointed party and the appointing party
exchange of information between prospective appointed parties on the same project,
exchange of information between interdependent projects;
exchange of information means of structuring and classifying information
exchange of information use of information during the operational phase of the asset.
exchange of information method of assignment for level of information need
How the information shall be presented as the infromaitn exchange? | What container (file) is this information in? | What is the current/ contract version? | Where is this infromaitn in the container (file)?
Purpose | Project's information production methods and procedures | Version | Title/Clause
Purpose | Reference information or shared resources provided by the appointing party | Version | Title/Clause
Purpose | Project Protocol | Version | Title/Clause
Information Protocol

## Supporting Information
Supporting Information
2.1 d) establish the supporting information
— existing asset information,
— shared resources,
— supporting documents or guidance material,
— references to relevant international, national or industry standards, and
— exemplars of similar information deliverables;
2.2 Assemble reference information and shared resources
— reference information or shared resources identified during project initiation;
— information generated during previous stages of the project; and
— the suitability for which the information can be used by the prospective lead appointed party.
1.6 Establish the project’s reference information and shared resources
a) existing asset information:
— from within the appointing party’s organization;
— from adjacent asset owners (utility companies, etc.);
— under license from external providers (mapping and imagery, etc.); and
— within public libraries and other sources of historical records.
b) shared resources, for example:
— process output templates (BIM execution plan, master information delivery plan, etc.);
— information container templates (2D/3D geometrical models, documents, etc.);
— style libraries (lines, text and hatch, etc.); or
— object libraries (2D symbols, 3D objects, etc.).
c) library objects defined within national and regional standards.
Information | Existing Asset information | Version | Clause/Sections
What information shall be used in the preparation of the project information? | What container (file) is this information in? | What is the current/ contract version? | Where is this information in the container (file)?
Information | Shared resources | Version | Clause/Sections
Applicable Industry standards | Titles | Version | Clause/Sections
I.S. ISO 19650-1 | Organization and digitization of information about buildings and civil engineering works, including building information modelling -- Information management using building information modelling: Concepts and principles | 2018
I.S. ISO 19650-2 | Organization and digitization of information about buildings and civil engineering works, including building information modelling -- Information management using building information modelling: Delivery phase of the assets | 2018
I.S. ISO 19650-3 | Organization and digitization of information about buildings and civil engineering works, including building information modelling -- Information management using building information modelling: Delivery phase of the assets | 2018
Uniclass 2015 Classification | Uniclass 2015 Classification
International Construction Measurement Standards (ICMS) | International Construction Measurement Standards (ICMS)
ISO 5500 | Asset management. Overview, principles and terminology | 2014
ISO 21502 | Project, programme and portfolio management. Guidance on project management | 2020
CEN-TR17654 | Guideline for the implementation of Exchange Information Requirements (EIR) and BIM Execution Plans (BEP) on European level based on EN ISO 19650-1 and -2 | 2021
| Exemplars | Version | Title/Clause

## Evaluation criteria
Tender response requirements and evaluation criteria
2.3 Establish tender response requirements and evaluation criteria
— the contents of the delivery team’s (pre-appointment) BIM execution plan;
— the competency of the prospective individuals undertaking the information management function on behalf of the delivery team;
— the prospective lead appointed party’s assessment of the delivery team’s capability and capacity;
— the delivery team’s proposed mobilization plan; and
— the delivery team’s information delivery risk assessment.
Tender Response Response | Evaluation criteria
That information that is expected to be returned by the tenderer. | What are the marks available for response or is this pass/Fail?
5.3.1 Functions (Information Management) | What are the marks available for response or Pass/Fail?
5.3.2 BEP (BIM execution plan) | What are the marks available for response or Pass/Fail?
a) information management function | What are the marks available for response or Pass/Fail?
b) information delivery strategy | What are the marks available for response or Pass/Fail?
c) Federation Strategy | What are the marks available for response or Pass/Fail?
d) high-level responsibility matrix, | What are the marks available for response or Pass/Fail?
e) proposed additions or amendments to the project’s information production methods and procedures | What are the marks available for response or Pass/Fail?
f) proposed additions or amendments to the project’s information standard | What are the marks available for response or Pass/Fail?
g) IT Resources | What are the marks available for response or Pass/Fail?
5.3.3/4 Capability and Capacity | What are the marks available for response or Pass/Fail?
5.3.5 Mobilization Plan | What are the marks available for response or Pass/Fail?
5.3.6 Risk Register (Information Management) | What are the marks available for response or Pass/Fail?

## IT solutions (hidden)
5.3.2 g) Information technology (IT)
Purpose | Delivery team | Software |  | Hardware | IT infrastructure
|  | Software | Versions | Specification | Architecture
CDE solution | General contractor/All appointed parties. | Information exchange software | xx.xx | PC/Laptop | on premise/cloud
Model authoring | Architectural | Authoring software - Architecture | xx.xx | PC/Laptop | on premise/cloud
Model authoring | Structural | Authoring software - Structural | xx.xx | PC/Laptop | on premise/cloud
Model authoring | MEP | Authoring software - MEP | xx.xx | PC/Laptop | on premise/cloud
Model checking | General contractor/Cross-disciplinary BIM manager. | Model coordination and checking software | xx.xx | PC/Laptop | on premise/cloud
Communication of model issues to authors. | General contractor/All appointed parties. | BIM collaboration software | xx.xx | PC/Laptop | on premise/cloud

## EIR_BEP (2) (hidden)
exchange information requirements/BIM execution plan
exchange information requirements | [11 empty] | BIM execution plan
information requirements | [5 empty] | level of information need |  | acceptance criteria |  | supporting information | exchange date or frequency | information delivery strategy |  |  |  | high-level responsibility matrix |  |  |  | proposed additions or amendments to the project’s
Type | Ref | Stage | Owner | Description | Creater | Document | Sections | project’s information standard, project’s information production methods and procedures, and reference information or shared resources | Template | existing asset information, shared resources, supporting documents or guidance material, references to relevant international, national or industry standards, and exemplars of similar information deliverables |  | Type | Ref | approach to meeting the exchange information requirements | Objectives/goals for the collaborative production | responsible | accountable | consulted | informed | information production methods and procedures | Template | information standard
Tracking Number |  | when | For who? | Why and what is the information needed? | By who? | What is the minimum amount of information needed for the appointing party to accept the requirements? |  | What conditions should be used to check the information deliverable in relation to consisancy, format/presentation, etc.? |  | What supporting material is needed to produce the information? | When the information is needed? | reference to EIR |  | how will the appointed party approach preparing the deliverable | what will the final deliverable achieve | author of the deliverable | approve the deliverable is fit for purpose | Consulted during production of the deliverable | Informed following deliverable completion | The methodology the Appointed party want to use to produce the deliverable (if differs from the Appointing party's IPMP) |  | Proposed alternatives by the Appointed party to the consistency of Project Information within the CDE